SPECIAL CONDITIONS

CONTENTS

These conditions amplify and supplement, if necessary, the General Conditions governing the Contract. Unless the Special Conditions provide otherwise, those General Conditions remain fully applicable. The numbering of the Articles of the Special Conditions is not consecutive but follows the numbering of the Articles of the General Conditions. In exceptional cases, and with the authorisation of the appropriate Commission departments, other clauses may be added to cover specific situations.

Article 2
Language of the Contract
2.1
The language used shall be English.

Article 4
Communications

4.1
Mr. Dorin Matveev, General Inspectorate for Emergency Situations of the Ministry of Internal Affairs, Republic of Moldova, no.69, Gheorghe Asachi str., Chisinau mun., MD2028, office nr.32, E-mail: logistica@dse.md. 

Article 7
Supply of documents

N/A
Article 8
Assistance with local regulations

Decision of the Government of the Republic of Moldova nr. 246 from 08.04.2010 regarding the application of the fiscal and customs facilities related to the implementation of the ongoing technical and investment assistance projects, which fall under the international treaties to which the Republic of Moldova is a party,  to allow full exemption from the following taxes: exempt from VAT with the right of deduction, exempt from excise duties, payment of customs tax, tax for carrying out customs procedures, tax for goods which, in the process of use, cause environmental pollution
Article 9
General Obligations

9.9
The Contractor to be put in place the specific activities to comply with minimum obligation toward visibility. These activities must comply with the rules lay down in the Communication and Visibility Manual for EU External Actions published on the EuropeAid Website: https://ec.europa.eu/europeaid/funding/communication-and-visibility-manual-eu-external-actions_en .
Article 10
Origin

10.1
All goods purchased must originate in a Member State of the European Union or a country covered by the ENI programme. For these purposes, ‘origin’ means the place where the goods are mined, grown, produced or manufactured and/or from which services are provided. The origin of the goods must be determined according to the EU Customs Code or to the relevant international agreement applicable.

Article 11
Performance guarantee

11.1
The amount of the performance guarantee shall be 5 % of the total Contract price, including any amounts stipulated in addenda to the Contract.
Article 12
Liabilities and Insurance

see provisions under General Conditions;
Article 13
Programme of implementation of tasks
13.2
The time limit within which the Contractor must submit for approval by the Project Manager of the programme of implementation is 15 days from the signing of the contract;
Article 14
Contractor’s drawings

14.1
Within a maximum of 45 days from the signing of the contract, the Contractor must submit to the Contracting Authority for approval a sketch (drawing) of distribution (placement) of all the equipment, installation and components on the special vehicle.
Before applying them, the Contractor must submit to the Contracting Authority for approval a sketch (drawing) of the external inscriptions and their color
Article 15
Sufficiency of tender prices


15.1
The contractor must provide in the cost of the offer, including the expenses (transport, accommodation, subsistence, entrance fees, etc.) related to a maximum one travel of a maximum of 2 representatives of the Contracting Authority at the place of production of the special vehicles, for the pre-reception process of the first prototype. 

At the same time, the Contractor must provide in the cost of the offer, including his own expenses related to training the personnel of the Contracting Authority, at the place of delivery of the special vehicles, in accordance with the provisions of the Technical Specifications.
Article 16
Tax and customs arrangements

16.1
The delivery conditions are DDP as mentioned in the GC 
Article 17
Patents and licences

17.1
see provisions under General Conditions;
Article 18
Commencement order 

18.1
The actions for implementation of the tasks must commence within a maximum of 5 days from the date of signing the contract;
Article 19
Period of implementation of the tasks

19.1
Maximum term of execution of the contract is 300 days from the date of signing the contract.
Article 24
Quality of supplies

24.2
The Contractor shall inform the Contracting Authority as soon as the first prototype of the special vehicle, made in accordance with the technical specifications, is ready, and shall ensure the visit of the representatives of the contracting authority to the place of production of the special vehicles, for a preliminary technical acceptance.
Article 25
Inspection and testing

25.2
Minimum  a one visit of representatives of the Contracting Authority will be undertaken at the place of production of the special vehicles, for the pre-acceptance (testing) process of the first prototype.
Article 26
General principles for payments
26.1
Payments shall be made in euros. However, if the contractor (the seller) it is a nationality from the Republic of Moldova, the payments will be made in MDL (Moldovan lei), according to the exchange rate established by the National Bank of Moldova on the date of the transfer.
Payment will be made based on any admissible invoice is, within 30 days from the moment of signing and registered it by the Contracting Authority. No pre-financing is foreseen.
Payments shall be authorised and made by The State Treasury of the Republic of Moldova or by the corresponding Bank.
26.3
By derogation, the final payment to the Contractor of the amounts due shall be made within 90 days after receipt by the Contracting Authority of an invoice and of the application for the certificate of provisional acceptance.
26.5
In order to obtain payments, the Contractor must forward to the authority referred to in paragraph 26.1 above:
a)
No pre-financing is foreseen. 
b)
For intermediate payments and final payment, the invoice(s), in triplicate, together with the request for provisional acceptance of the supplies.

26.9
For the execution of this contract, no price revisions can be foreseen.
Article 28
Delayed payments

28.2
By derogation from Article 28.2 of the General Conditions, once the deadline laid down in Article 26.3 has expired, the Contractor shall, upon demand, be entitled to late-payment interest at the rate and for the period mentioned in the General Conditions. The demand must be submitted within two months of receiving late payment.
Article 29
Delivery

29.3
The packaging shall become the property of the recipient subject to environmental considerations.

29.5/6/7
Any delivery will be accompanied by the invoice in three copies, the document of delivery-receipt in three copies, the technical documentation, the service and guarantee books, operating instructions and other documents provided in the technical specification or in the Contract.
Article 31
Provisional acceptance

The Certificate of Provisional Acceptance must be issued using the template in Annex C11. Provisional acceptance will be made in accordance with the provisions of the technical specification.
Article 32
Warranty obligations
32.6
The warranty obligations shall be stipulated in the technical specifications;
32.7
The warranty must remain valid for period to be stipulated in the technical specifications, after provisional acceptance.
Article 33
After-sales service

33.1
Any after-sales service that the Contractor must provide refers to the warranty period of the product (s), according to the provisions of the technical specification.
Article 40
Settlement of disputes

40.4
Any dispute arising out of or relating to this Contract which cannot be settled otherwise shall be referred to the exclusive jurisdiction of the specialized courts of the Republic of Moldova, according to the competence, in accordance with the national legislation of the state of the Contracting Authority.
* * *

1
2006


















2
15 January 2016
Page 4 of 4
c4d_specialconditions_en.doc

